## Sheet1
[7 empty] | Status | Description | Total Completion | Total In-Progress
Satellite Management Game | [8 empty] | 22.95% | 1.639%
| Main Menu | [7 empty] | Total tasks
|  | UI | [6 empty] | 122
|  |  | New Game | [5 empty] | Complete
|  |  |  | art |  |  |  |  | 28
start new game
initialize world
start intro events
Load game
art
load from save file
Settings
art
volume
resolution
units
quit
art
exit program
Integration
Background
Music
Integration
Gameplay
|  | Lighting |  |  |  |  | 1 | some light behind earth/satellites - not realistic but helpful
|  | Sun model | [5 empty] | texture
|  |  | rotate around earth |  |  |  |  | simulate earth's movement
|  | Earth |  |  |  |  | 1 | texture
|  | Earth rotation |  |  |  |  | 1
|  | create new satellite |  |  |  |  | 0
|  |  | payloads |  |  |  | 0 | select payload
|  |  | fuel |  |  |  | 1 | measure fuel in deltaV. deltaV = exhaust exit speed -> total propelant mass of 1.7 x vehicle dry mass
|  |  | ui |  |  |  | 1
|  |  | orbit selection |  |  |  | 1 | pick an orbit (LEO, MEO, GTO) within certain inclinations. higher orbits more expensive
|  |  | cost |  |  |  |  | total cost of system and launch
Launch
|  |  |  | graphics |  |  |  | small animation
|  |  |  | create game object |  |  | 1 | creat game object from prefab
adjust graphics of new sat
add sat to list
satellites in orbit
|  |  | generic model |  |  |  | 1
|  |  | imagery model |  |  |  | 1
|  |  | display orbit path |  |  |  | 1
|  |  | display position |  |  |  | 1 | highlight current position, trail length based on game speed
satellite management
|  |  |  | satellite List |  |  | 1
[5 empty] | array of satellites |  | 1 | lists all satellites
[5 empty] | select to highlight |  | 1 | checkbox for details, highlight for orbit, dont show details if no selection
[5 empty] | formatting & style |  | 1 | checkbox graphics
[5 empty] | swap details/show orbit boxes |  | 1 | make show orbit be the checkbox and click the name to show details
task payload
data relay
on/off
imagery
image area
experiment
when to run
grapple arm
go-ahead
|  |  |  | maneuver |  |  | 1
[5 empty] | UI |  | 1 | select direction & deltaV [prograde/retrograde, normal/antinormal]
[5 empty] | update velocity |  | 1 | apply deltaV in direction, over the course of 1sec. All satellites get the same maneuver engines
[5 empty] | ghost |  | 1 | while setting maneuvers, show a ghost of the orbit after the maneuver
|  |  |  | view telemetry |  |  | 1 | orbital elements
|  |  |  | alternative tlm |  |  | 1 | alternative orbital elemnts if circular, i=0, etc.
|  |  |  | view health |  |  |  | fuel level, battery, etc.
|  |  | integration |  |  |  |  | bug fixes
|  |  | satellite motion |  |  |  | 1
sat de-orbit mechanics
burn-up at x km
atmospheric drag
|  | camera controls |  |  |  |  | 1
|  |  | rotate about focus |  |  |  | 1 | right-mouse & drag
|  |  | switch focus |  |  |  |  | satellites or earth
event system
debris
graphics
probability to destroy satellite
|  |  | other satellites |  |  |  |  | chance to put a satellite in a random orbit. can view tlm but no control
space wx
CME event
impact on satellites
graphics
UI
describe event
show impact
mission system
probability to give mission
continuous missions
data relay
lat/long for customer
channel/speed required
one time missions
ground imagery
lat/long
satellite imagery
target satellite
experiment
experimental payload
de-orbit
target satellite
rendevous
target satellite
$ reward based on mission difficulty
UI
available missions
description
add to active
|  |  |  | active missions |  |  |  | completed artwork/design
|  |  |  | completed |  |  |  | basic buttons
|  |  | Time-scaling |  |  |  | 1
|  |  |  | UI |  |  | 1
|  |  |  | functionality |  |  | 1
Integration
pause menu
save
settings
return to main menu
quit
Graphics rework
ui