## Sheet1
[6 empty] | Status | Description | Total Completion | Total In-Progress
Satellite Management Game | [7 empty] | 35.38% | 1.538%
| Main Menu | [6 empty] | Total tasks
|  | UI | [5 empty] | 130
|  |  | New Game |  |  |  |  | Complete
|  |  |  | art |  |  |  | 46
start new game
initialize world
start intro events
Load game
art
load from save file
Settings
art
volume
resolution
units
quit
art
exit program
Background
Music
Gameplay
|  | Lighting |  |  |  | 1 | some light behind earth/satellites - not realistic but helpful
|  | Sun model |  |  |  |  | texture
|  |  | rotate around earth |  |  |  | simulate earth's movement
|  | Earth |  |  |  | 1 | texture
|  | Earth rotation |  |  |  | 1
create new satellite
|  |  | payloads |  |  |  | select payload
|  |  | fuel |  |  | 1 | measure fuel in deltaV. deltaV = exhaust exit speed -> total propelant mass of 1.7 x vehicle dry mass
|  |  | ui |  |  | 1
error messages
|  |  | orbit selection |  |  | 1 | pick an orbit (LEO, MEO, GTO) within certain inclinations. higher orbits more expensive
|  |  | cost |  |  |  | total cost of system and launch
Launch
|  |  |  | graphics |  |  | small animation
|  |  |  | create game object |  | 1 | creat game object from prefab
|  |  |  | add sat to list |  | 1
satellites in orbit
|  |  | generic model |  |  | 1
|  |  | imagery model |  |  | 1
|  |  | display orbit path |  |  | 1
|  |  | display position |  |  | 1 | highlight current position, trail length based on game speed
satellite management
|  |  |  | satellite List |  | 1
[5 empty] | array of satellites | 1 | lists all satellites
[5 empty] | select to highlight | 1 | checkbox for details, highlight for orbit, dont show details if no selection
[5 empty] | formatting & style | 1 | checkbox graphics
[5 empty] | swap details/show orbit boxes | 1 | make show orbit be the checkbox and click the name to show details
|  |  |  | task payload |  |  | payloads should be scripts that are attached
[5 empty] | data relay | 1 | passive
[5 empty] | show beam coverage | 1 | must check if view is limited by sensor area or horizon
[5 empty] | imagery | 1 | mission must be in footprint, cooldown timer on completing missions
[5 empty] | show imagery area | 1 | copy FOV from data relay
[5 empty] | experiment |  | run
[5 empty] | grapple arm |  | attach/detach
|  |  |  | maneuver |  | 1
[5 empty] | UI | 1 | select direction & deltaV [prograde/retrograde, normal/antinormal]
[5 empty] | update velocity | 1 | apply deltaV in direction, over the course of 1sec. All satellites get the same maneuver engines
[5 empty] | ghost | 1 | while setting maneuvers, show a ghost of the orbit after the maneuver
|  |  |  | view telemetry |  | 1 | orbital elements
|  |  |  | alternative tlm |  | 1 | alternative orbital elemnts if circular, i=0, etc.
|  |  |  | view health |  | 1 | fuel level, other health as added
|  |  | satellite motion |  |  | 1
|  |  | sat de-orbit mechanics |  |  | 1
|  |  |  | destroy on touch earth |  | 1
|  |  |  | atmospheric drag |  | 1
|  | camera controls |  |  |  | 1
|  |  | rotate about focus |  |  | 1 | right-mouse & drag
|  |  | switch focus |  |  |  | satellites or earth
event system
debris
graphics
probability to destroy satellite
|  |  | other satellites |  |  |  | chance to put a satellite in a random orbit. can view tlm but no control
space wx
CME event
impact on satellites
graphics
UI
describe event
show impact
mission system
|  |  | timer to give new missions |  |  | 1 | timer set to random time within range
|  |  | mission type |  |  | 1 | chance for each mission type
data relay
[5 empty] | initialize points | 1
[5 empty] | display points | 1
[5 empty] | reward | 1
list integration
|  |  |  | ground imagery |  |  | copy from data relay, only 1 point
[5 empty] | lat/long | 1
[5 empty] | reward | 1
list integration
satellite imagery
target satellite
reward
list integration
experiment
experimental payload
reward
list integration
de-orbit
target satellite
reward
list integration
rendevous
target satellite
reward
list integration
|  |  | UI |  |  | 0
selected mission details
|  |  |  | available missions |  | 0
[5 empty] | missions are added to list | 1
select to view parameters
[5 empty] | highlight points when selected | 1
show reward
|  |  | Time-scaling |  |  | 1
|  |  |  | UI |  | 1
|  |  |  | functionality |  | 1
pause menu
save
settings
return to main menu
quit
Graphics rework
|  | ui |  |  |  |  | 80/90s asthetic - win95 style
|  | lighting |  |  |  |  | dark side of earth needs to be visible
Refactor/Performance Pass
|  | cache GetComponent<>() calls |  |  |  |  | reduce the number of GetComponent calls as much as possible