## Sheet1
[7 empty] | Status | Description | Total Completion | Total In-Progress
Satellite Management Game | [8 empty] | 26.89% | 3.361%
| Main Menu | [7 empty] | Total tasks
|  | UI | [6 empty] | 119
|  |  | New Game | [5 empty] | Complete
|  |  |  | art |  |  |  |  | 32
start new game
initialize world
start intro events
Load game
art
load from save file
Settings
art
volume
resolution
units
quit
art
exit program
Integration
Background
Music
Integration
Gameplay
|  | Lighting |  |  |  |  | 1 | some light behind earth/satellites - not realistic but helpful
|  | Sun model | [5 empty] | texture
|  |  | rotate around earth |  |  |  |  | simulate earth's movement
|  | Earth |  |  |  |  | 1 | texture
|  | Earth rotation |  |  |  |  | 1
create new satellite
|  |  | payloads |  |  |  | 0 | select payload
|  |  | fuel |  |  |  | 1 | measure fuel in deltaV. deltaV = exhaust exit speed -> total propelant mass of 1.7 x vehicle dry mass
|  |  | ui |  |  |  | 1
error messages
|  |  | orbit selection |  |  |  | 1 | pick an orbit (LEO, MEO, GTO) within certain inclinations. higher orbits more expensive
|  |  | cost |  |  |  |  | total cost of system and launch
Launch
|  |  |  | graphics |  |  |  | small animation
|  |  |  | create game object |  |  | 1 | creat game object from prefab
|  |  |  | add sat to list |  |  | 1
satellites in orbit
|  |  | generic model |  |  |  | 1
|  |  | imagery model |  |  |  | 1
|  |  | display orbit path |  |  |  | 1
|  |  | display position |  |  |  | 1 | highlight current position, trail length based on game speed
satellite management
|  |  |  | satellite List |  |  | 1
[5 empty] | array of satellites |  | 1 | lists all satellites
[5 empty] | select to highlight |  | 1 | checkbox for details, highlight for orbit, dont show details if no selection
[5 empty] | formatting & style |  | 1 | checkbox graphics
[5 empty] | swap details/show orbit boxes |  | 1 | make show orbit be the checkbox and click the name to show details
|  |  |  | task payload |  |  |  | payloads should be scripts that are attached
[5 empty] | data relay |  | 0 | passive
[5 empty] | imagery |  | 0
[6 empty] | show area to image |  | cone from satellite to target
[5 empty] | experiment |  |  | run
[5 empty] | grapple arm |  |  | attach/detach
|  |  |  | maneuver |  |  | 1
[5 empty] | UI |  | 1 | select direction & deltaV [prograde/retrograde, normal/antinormal]
[5 empty] | update velocity |  | 1 | apply deltaV in direction, over the course of 1sec. All satellites get the same maneuver engines
[5 empty] | ghost |  | 1 | while setting maneuvers, show a ghost of the orbit after the maneuver
|  |  |  | view telemetry |  |  | 1 | orbital elements
|  |  |  | alternative tlm |  |  | 1 | alternative orbital elemnts if circular, i=0, etc.
|  |  |  | view health |  |  |  | fuel level, battery, etc.
|  |  | satellite motion |  |  |  | 1
sat de-orbit mechanics
|  |  |  | destroy on touch earth |  |  | 1
|  |  |  | atmospheric drag |  |  | 1
|  | camera controls |  |  |  |  | 1
|  |  | rotate about focus |  |  |  | 1 | right-mouse & drag
|  |  | switch focus |  |  |  |  | satellites or earth
event system
debris
graphics
probability to destroy satellite
|  |  | other satellites |  |  |  |  | chance to put a satellite in a random orbit. can view tlm but no control
space wx
CME event
impact on satellites
graphics
UI
describe event
show impact
mission system
|  |  | timer to give new missions |  |  |  | 1 | timer set to random time within range
|  |  | mission type |  |  |  | 0 | chance for each mission type
continuous missions
data relay
lat/long for customer
channel/speed required
one time missions
ground imagery
lat/long
satellite imagery
target satellite
experiment
experimental payload
de-orbit
target satellite
rendevous
target satellite
$ reward based on mission difficulty
UI
available missions
description
add to active
|  |  |  | active missions |  |  |  | completed artwork/design
|  |  |  | completed |  |  |  | basic buttons
|  |  | Time-scaling |  |  |  | 1
|  |  |  | UI |  |  | 1
|  |  |  | functionality |  |  | 1
Integration
pause menu
save
settings
return to main menu
quit
Graphics rework
|  | ui | [5 empty] | 80/90s asthetic - win95 style